## Sheet1
Risk managmemt
Key: | Impact Category: | Impact Values | Likelihood Category: | Likelihood Values
| Negligable | 1,2 | Unlikely | 1,2
| Marginal | 3,4,5 | Possible | 3,4,5
| Critical | 6,7,8 | Likely | 6,7,8
| Catastrophic | 9,10 | Very Likely | 9,10
Scenario | Description of potential impact | Impact Value (1-10) | Likelihood Value (1-10) | Risk Exposure (%) | Management (Combat Plan/POA) | Current Control | Futher Action Necessary (Y/N) | Who (Members involved in this scenario) | Due Date | Status | Reviewed Date
Team members may tend to have unclear goals. | If the problem statement and goals are unknown, brainstorming ideas will be a complex task to achieve. | 9 | 5 | 45% | Make sure everyone's clear on the goals and reasoning of the application. |  | N | 4 | 2021-03-04 | Done | 2021-03-06
Minimal skilled expertise | Each member of the group may have different amount of experience in various fields. | 5 | 3 | 15% | Ask everyone which mission they are comfortable working with. |  | N | 4 | 2021-03-04 | Done | 2021-03-06
Limited ideas | Not much research done on current-state of the art tehcnology. | 2 | 7 | 14% | Try to research as much as possible using various sources of information. |  | N | 1 | 2021-03-04 | Done | 2021-03-06